## TaskList
Task Name | Estimate time( hour) | Taken by | Actual Time | Status | Date Doing | Note | Problem
Requirement analyze | 16 | Nguyen Van A | 20 | Done
[Report 1] Project Information | 2 | Nguyen Van A |  | Done
[Report 1] Introduction | 2 | Nguyen Van A |  | Done
[Report 1] Current Situation | 2 | Nguyen Van A |  | Done
[Report 1] Problem Definition | 2 | Nguyen Van A |  | Done
Draw ERD diagram | 8 | Nguyen Van A |  | Done
Deploy database to AWS (empty database) | 4 | Nguyen Van A |  | Done
Learning ReactJS | 10 | Nguyen Van A |  | Done
Total | 46 |  | 93.88%
Requirement analyze | 12 | Nguyễn Van B |  | Done
[Report 1] Proposed Solution | 2 | Nguyễn Van B |  | Done
[Report 1] Functional Requirement | 5 | Nguyễn Van B |  | Done
[Report 1] Roles and Responsibility | 2 | Nguyễn Van B |  | Done
Learning Spring for Restful API | 10 | Nguyễn Van B |  | Done
Learning Spring Security | 10 | Nguyễn Van B |  | Done
Draw Usecase Diagram | 14 | Nguyễn Van B |  | Done
Total | 55 |  | 112.2%
[UI Mockup Web] Login/Register Screen | 3 | Nguyễn Van C | 3 | Done
[UI Mockup Web] Home (Item Listing) Screen | 4 | Nguyễn Van C |  | Done
[UI Mockup Web] Auction posting screen | 3 | Nguyễn Van C |  | Done
[UI Mockup Web] Item Screen | 4 | Nguyễn Van C |  | Done
[UI Mockup Web] Cart Screen | 5 | Nguyễn Van C |  | Done
[UI Mockup Web] Checkout Screen | 5 | Nguyễn Van C |  | Done
[UI Mockup Web] Personal Item Screen | 5 | Nguyễn Van C |  | Done
[UI Mockup Web] Notification screen | 5 | Nguyễn Van C |  | Done
[UI Mockup Web] Admin's auction management screen | 5 | Nguyễn Van C |  | Done
[UI Mockup Web] Admin's user management screen | 5 | Nguyễn Van C |  | Fail
[UI Mockup Web] Admin's category management screen | 5 | Nguyễn Van C |  | Done
[UI Mockup Web] Admin's Report screen | 4 | Nguyễn Van C |  | Done
Requirement analyze | 8 | Nguyễn Van C |  | Done
Total | 61 |  | 124.5%